## Product Backlog
Distributed Pacman Product Backlog
| Task ID | Story / Description | Priority | Estimate | Points Left After Sprint
[5 empty] | 1 | 2 | 3 | 4 | 5
Sprint 1 | 1 | Implementazione struttura del game model | 2 | 8 | 0 | - | - | - | -
| 2 | Comportamento in prolog | 1 | 8 | 0 | - | - | - | -
| 3 | Implementazione di una prima versione del controller del client di una partita in single player | 3 | 10 | 5 | 0 | - | - | -
| 4 | GUI Versione Base (Single Player) | 4 | 10 | 4 | 0 | - | - | -
Sprint 2 | 5 | Completamento del model e prima versione funzionante | 5 | 10 | 10 | 2 | 0 | - | -
Sprint 3 | 6 | Struttura ad attori del Client | 6 | 10 | 10 | 10 | 0 | - | -
| 7 | Server : Struttura ad attori | 7 | 25 | 25 | 25 | 2 | - | -
| 8 | Model della parte di comunicazione e integrazione | 10 | 7 | 7 | 7 | 2 | - | -
| 9 | Integrazione view - controller | 11 | 15 | 15 | 15 | 5 | 0 | -
| 10 | Comunicazione Message Passing Client-Server | 9 | 8 | 8 | 8 | 0 | - | -
| 11 | Comunicazione Peer to Peer | 8 | 30 | 30 | 30 | 5 | 0 | -
Sprint 4 | 12 | Server: Implementazione del comportamento | 14 | 20 | 20 | 20 | 20 | 4 | 0
| 13 | Completamento modello MVC | 15 | 12 | 12 | 12 | 12 | 0 | -
| 14 | Completamento della comunicazione p2p | 12 | 15 | 15 | 15 | 15 | 4 | 0
| 15 | Completamento della comunicazione client-server | 13 | 10 | 10 | 10 | 10 | 0 | -
Sprint 5 | 16 | Server: Database | 16 | 5 | 5 | 5 | 5 | 5 | 0
| 17 | Server: Automazione e miglioramenti | 17 | 5 | 5 | 5 | 5 | 5 | 0
| 18 | Revisione e integrazione | 18 | 10 | 10 | 10 | 10 | 10 | 0
| 19 | Test & Bug Fixing | 19 | 10 | 10 | 10 | 10 | 10 | 0
|  |  |  | 228 | 201 | 184 | 101 | 38 | 0
|  |  |  | Consumed: | 27 | 17 | 83 | 63 | 38

## Design Backlog
|  | Start up project and design | start on 15/06 | Duration: 10 Days
ends on 24/6
Priority | Product Backlog Item | Sprint Task | Volunteer | Initial Estimate | Points Left after Days
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
2 | setting up the build environment | Create Repository on GitHub | Manuel | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create gradle project | Manuel | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Setup the build & config it for Travis | Manuel | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | setup branch for GitFlow process | Manuel | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
|  | setup project for code quality tools | Manuel | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
1 | Design Arghitecture of the System & Distribution model | Design the app general structure | All | 7 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 0
|  | Design the client-side general structure | Giulia - Chiara | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | 1 | 1 | 0
|  | Design the server-side general structure | Manuel - Fede - Marghe | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 2 | 1
|  | Design the integration of different parts | All | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2
|  | Design the model of distribution | All | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0
|  |  |  | 30 | 27 | 27 | 24 | 24 | 19 | 18 | 18 | 17 | 15 | 3
[12 empty] | remaining: |  | 3
25

## Sprint Backlog S1
|  | Sprint 1 - Base Game | start on 24/06 | Duration: 13 Days |  |  |  |  | Expected Product : |  |  |  | A first working version of the game in his classic version (One player in a standalone pc)
|  |  | ends on 06/07 | sprint retrospective | http://goo.gl/G81jQs
Priority | Product Backlog Item | Sprint Task | Volunteer | Initial Estimate | Points Left after Days
[5 empty] | 2017-06-24 | 2017-06-25 | 2017-06-26 | 2017-06-27 | 2017-06-28 | 2017-06-29 | 2017-06-30 | 2017-07-01 | 2017-07-02 | 2017-07-03 | 2017-07-04 | 2017-07-05 | 2017-07-06
2 | game model design implementation | Character side model | Giulia | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Game Item side model | Bottax | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Character side model test | Giulia | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Game Item side model test | Bottax | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Javadoc | Giulia - Bottax | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
1 | Prolog Behaviour implementation | Prolog Behaviour Impl | Marghe - Fede - chiara | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
|  | Java/Scala - Prolog interaction | Giulia | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0
3 | Single player Client controller Design and implementation | User Interaction | Bottax | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1
|  | Character Behaviour controller | Marghe | 4 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
|  | Match controller |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2
4 | Single player Gui | "Application" Gui | Chiara | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 3
|  | Game Gui | Chiara | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0
|  | Mapping playground into Gui | Bottax - Chiara | 6 | 6 | 6 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1
|  | founding graphical resource | Bottax - Chiara | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 41 | 38 | 38 | 37 | 36 | 35 | 26 | 24 | 21 | 19 | 18 | 16 | 14 | 11
[16 empty] | Remaining: | 11

## Sprint Backlog S2
|  | Sprint 2 - Base Game | Starts on 06/07/2017 | Duration: 7 Days |  | Expected Product : |  |  |  | A first working version of the game in his classic version (One player in a standalone pc)
|  |  | ends on 13/07 | sprint retrospective | https://goo.gl/dkdxWN
Priority | Product Backlog Item | Sprint Task | Volunteer | Initial Estimate | Points Left after Days
|  |  |  | 2017-07-06 | 2017-07-07 | 2017-07-08 | 2017-07-09 | 2017-07-10 | 2017-07-11 | 2017-07-12 | 2017-07-13
1 | Game model and view completion | Character side model | Giulia - Fede | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0
|  | Game Item side model | Marghe | 4 | 4 | 3 | 3 | 2 | 1 | 1 | 0
|  | View Completion | Bottax - Chiara | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
|  | Test | Fede | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0
|  | Javadoc | All | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
2 | test and deploy | Match Test | Fede | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2
|  | deploy of a working version | All | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2
|  |  |  | 24 | 24 | 23 | 20 | 16 | 12 | 8 | 4
[10 empty] | Remaining: | 4

## Sprint Backlog S3
|  | Sprint 3 - First Communication | Starts on 13/07/2017 | Duration: 12 Days |  | Expected Product : |  |  |  | A first working version of the game in his classic version (One player in a standalone pc) + a communicating client - server architecture
|  |  | ends on 26/07 | sprint retrospective | https://goo.gl/3vt1Gs
Priority | Product Backlog Item | Sprint Task | Volunteer | Initial Estimate | Points Left after Days
|  |  |  | 2017-07-13 | 2017-07-14 | 2017-07-15 | 2017-07-16 | 2017-07-17 | 2017-07-18 | 2017-07-19 | 2017-07-20 | 2017-07-21 | 2017-07-22 | 2017-07-23 | 2017-07-24 | 2017-07-25 | 2017-07-26
0 | - | Complete Previous left task | All | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Client Actor system | study of the problem and design | Giulia | 3 | 2 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actor System creation | Giulia | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 0
|  | Simple message exchange between actors | Giulia | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0
1 | Server Actor system | study of the problem and design | Bottax | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actor System creation | Bottax | 10 | 10 | 10 | 8 | 7 | 4 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0
|  | Simple message exchange between actors | Bottax | 5 | 5 | 5 | 5 | 4 | 3 | 3 | 2 | 2 | 2 | 1 | 0 | 0 | 0
2 | Communication model and integration | Integration between Actors and client MVC structure | Giulia | 5 | 5 | 5 | 5 | 8 | 8 | 7 | 6 | 6 | 5 | 4 | 3 | 1 | 0
|  | design of the message exchange protocoll | Bottax - Giulia | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 5 | 5 | 4 | 4
|  | Implementation of the exchange protocoll | Bottax - Giulia | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 7
2 | Message Passing communication for Client-Server | Configuration of server | Bottax | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | Configuration of client | Giulia | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
|  | communication test | Bottax - Giulia | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
3 | View - Controller integration | Integration of controller and view | Marghe - Chiara | 10 | 9 | 9 | 9 | 8 | 7 | 6 | 4 | 4 | 3 | 3 | 3 | 3 | 2
|  | Controller improving | Marghe - Chiara | 10 | 10 | 10 | 9 | 9 | 8 | 7 | 7 | 6 | 5 | 3 | 2 | 1 | 1
|  | View Improving | Marghe - Chiara | 10 | 10 | 9 | 9 | 8 | 6 | 6 | 5 | 4 | 4 | 4 | 3 | 3 | 2
4 | Peer to Peer Communication | study of the problem and design | Fede | 10 | 9 | 9 | 8 | 7 | 6 | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 2
|  | Creation of the peer structure | Fede | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 6 | 5 | 4 | 3 | 1 | 0 | 0
|  | creation of the internal peer structure ( server - clients) | Fede | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 9 | 8 | 7 | 6 | 5 | 4 | 3
|  |  |  | 68 | 63 | 62 | 60 | 59 | 53 | 48 | 43 | 42 | 33 | 26 | 20 | 15 | 13
[16 empty] | Remaining: | 13

## Sprint Backlog S4
|  | Sprint 4 - Communication Setup | Starts on 26/07/2017 | Duration: 15 Days |  | Expected product: |  |  | a working local version of the game + a communicating system
|  |  | ends on 09/08 | sprint retrospective | https://goo.gl/Ncq82w
Priority | Product Backlog Item | Sprint Task | Volunteer | Initial Estimate | Points Left after Days
|  |  |  | 2017-07-26 | 2017-07-27 | 2017-07-28 | 2017-07-29 | 2017-07-30 | 2017-07-31 | 2017-08-01 | 2017-08-02 | 2017-08-03 | 2017-08-04 | 2017-08-05 | 2017-08-06 | 2017-08-07 | 2017-08-08 | 2017-08-09
3 | Server behaviuor implementation | Implementation of functionality | Bottax | 20 | 18 | 18 | 17 | 15 | 15 | 15 | 14 | 12 | 8 | 8 | 8 | 5 | 4 | 4
|  | test with fake client | Bottax | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 1 | 0
1 | MVC Model | Complete integration for model-controller | Marghe-Chiara | 5 | 5 | 5 | 5 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | complete integration for view-controller | Marghe-Chiara | 5 | 5 | 5 | 5 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | complete integration | Marghe-Chiara | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Peer-toPeer communication | P2P configuration | Fede | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | P2P communication | Fede | 7 | 7 | 6 | 6 | 5 | 3 | 3 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0
|  | fake (local) communication test | Fede | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
|  | real (distributed) communication test | Fede | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 5 | 5 | 4
2 | Client- server communication | Implemetation of message exchange protocol | Giulia | 8 | 8 | 7 | 7 | 6 | 5 | 5 | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0
|  | integration with controller's object | Giulia | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0
|  | communication test | Giulia | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0
|  |  |  | 68 | 66 | 63 | 62 | 56 | 52 | 46 | 39 | 34 | 28 | 23 | 17 | 13 | 11 | 8
[17 empty] | Remaining: | 8

## Sprint Backlog S5
|  | Sprint 5 - Integration & Test | starts on 09/08 | Duration: 14 Days |  | Expected Product : |  |  |  | A working demo version of the game
|  |  | ends on |  | sprint retrospective | goo.gl/j8gjYV
Priority | Product Backlog Item | Sprint Task | Volunteer | Initial Estimate | Points Left after Days
|  |  |  | 2017-08-09 | 2017-08-10 | 2017-08-11 | 2017-08-12 | 2017-08-13 | 2017-08-14 | 2017-08-15 | 2017-08-16 | 2017-08-17 | 2017-08-18 | 2017-08-19 | 2017-08-20 | 2017-08-21 | 2017-08-22
1 | Server: Database | Creation of the Database | Giulia | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Database query method | Giulia | 4 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | integration with actor system | Bottax | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Server automation and improvement | server automatic configuration | Bottax | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | refactor and testing | Bottax | 5 | 5 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0
2 | Integration and test | model test | All | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0
|  | view test | All | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 2 | 1
|  | controller test | All | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 1 | 2 | 1 | 1 | 1
|  | p2p communication test | All | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 1
|  | client-server communication test | All | 2 | 2 | 2 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0
|  | server test | All | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1
Deadline
|  |  |  | 30 | 27 | 23 | 18 | 17 | 15 | 11 | 11 | 10 | 9 | 7 | 4 | 0 | 0
[16 empty] | Remaining: | 0